## EcoGrow Audit Matrix
AUD-01 | Requirements baseline | Requirements Engineering; Governance Pack RTM | Requirement IDs trace consistently into RTM, Epic Catalogue and Jira. | FR-01 to FR-09 are established; requirement IDs are carried into Jira mappings. | GREEN | No material traceability break identified. | Preserve requirement IDs unchanged through delivery. | BA / Governance
AUD-02 | FR-05 / ECO-7 traceability | RTM row US-03; DEC-03; Jira ECO-7 evidence supplied | FR-05 must trace to BO-03, FEAT-03, US-03/ECO-7 and have concrete ACs. | FR-05 / ECO-7 acceptance evidence now available and reviewed. | GREEN | AC1–AC3 passed in the controlled portfolio prototype; evidence is attached to Jira ECO-7 and Sprint Review/persona outcome is recorded. | Retain evidence; do not mark RTM Validated until the remaining governance/DoD gate is satisfied. / QA + BA | QA / BA
AUD-03 | FR-06 / ECO-8 traceability | RTM row US-04; DEC-04; Jira ECO-8 evidence supplied | FR-06 must trace to BO-03, FEAT-04, US-04/ECO-8 and have concrete ACs. | FR-06 / ECO-8 acceptance evidence now available and reviewed. | GREEN | AC1–AC3 passed in the controlled portfolio prototype; evidence is attached to Jira ECO-8 and Sprint Review/persona outcome is recorded. | Retain evidence; do not mark RTM Validated until the remaining governance/DoD gate is satisfied. / QA + BA | QA / BA
AUD-04 | FR-08 / ECO-10 traceability | RTM row US-06; Jira ECO-10 evidence | FR-08 must support BO-04 with usage events across all three capabilities. | FR-08 / ECO-10 acceptance evidence now available; overall governance validation remains open. | GREEN | Canonical ECO-10 prototype demonstrates Plant Library and Harvest Tracker usage-event capture (2 of 3 core capabilities); supplementary Community Forum evidence completes the third capability. Together, the evidence covers the FR-08 three-capability requirement. Timestamp, capability tag, Recorded status and no separate opt-in were evidenced. Jira ECO-10 is In Review with video evidence attached. | Complete remaining governance/DoD gate before Done/RTM validation. / Delivery + QA | Delivery / QA
AUD-05 | ECO-7 acceptance evidence | Jira ECO-7; Section 7; carryover validation checklist | Acceptance criteria pass in a test environment with evidence. | ECO-7 acceptance evidence is now available. | GREEN | The earlier missing-evidence finding is resolved by the ECO-7 prototype demonstration, AC1–AC3 PASS results, attachments, and Jira review history. | Do not round story-level evidence into final MVP acceptance; continue through governance closeout. / QA + BA | QA / BA
AUD-06 | ECO-8 acceptance evidence | Jira ECO-8; Section 7 | Acceptance criteria pass in a test environment with evidence. | ECO-8 acceptance evidence is now available. | GREEN | The earlier missing-evidence finding is resolved by the ECO-8 prototype demonstration, AC1–AC3 PASS results, attachments, and Jira review history. | Do not round story-level evidence into final MVP acceptance; continue through governance closeout. / QA + BA | QA / BA
AUD-07 | Workflow gate | Jira Build Specification; current Jira board screenshot | In Progress → In Review/QA for acceptance testing → Done only after Definition of Done. | ECO-7, ECO-8 and ECO-10 are In Review after evidence-led acceptance testing. | GREEN | The In Review/QA gate has now been exercised for the Sprint 2 stories; none has been moved to Done prematurely. | Keep stories In Review until the remaining Definition-of-Done/governance conditions are evidenced. / Scrum Master + QA | Scrum Master / QA
AUD-08 | Definition of Done | Requirements Engineering §3.9; Jira Build Specification §9 | ACs pass; Sprint Review demonstration; usage event confirmed where applicable; RTM updated to Validated. | None of these delivery-validation gates are yet evidenced for Sprint 2. | Acceptance and story-level review evidence now exists for ECO-7/ECO-8/ECO-10; complete DoD is not yet evidenced. | AMBER | AC testing and Jira review/persona outcomes are recorded, but the source DoD also requires RTM validation and, where applicable, reporting-layer confirmation. Formal all-persona Sprint Review evidence is not independently evidenced. | Complete the remaining DoD/RTM gate from actual evidence; do not mark Done by status alone. / BA + QA + PO
AUD-09 | Sprint Review evidence | Section 7 Business Validation & Product Acceptance; Confluence Build Spec | Formal Sprint Review evidence is distinct from per-story checkpoints. | No formal Sprint Review evidence exists yet; Section 7 explicitly keeps Sprint 2 forward-looking. | Story-level Sprint Review/persona evidence is recorded; formal all-persona meeting record is not evidenced. | AMBER | ECO-7, ECO-8 and ECO-10 each have Jira review comments and a Product Owner Persona outcome, but the source framework describes a formal Sprint Review with the planned personas and a dated record. | Use the Jira comments as the documented fallback and explicitly label the evidence as a portfolio persona review; do not claim an independent external stakeholder meeting. / BA + PO
AUD-10 | Confluence workspace | Confluence/Miro/Lucidchart/Power BI Build Specification; user's current Jira Docs screenshot | Confluence is the durable project record; Meeting Notes are created per real meeting. | Jira Docs shows 'Try Confluence now' / no connected Confluence space. | Confluence remains unconfigured; Jira is being used as the documented fallback. | AMBER | The durable Confluence layer is still not configured. Story-level Sprint 2 review evidence has been recorded in Jira instead. | Preserve the fallback honestly; do not imply Confluence meeting notes exist. / BA + Admin
AUD-11 | Development / source control | User's Jira Development screenshot | Source-control linkage is optional to the BA governance model but useful for a live implementation portfolio. | Jira Development shows Source code management not set up; GitHub/Bitbucket/GitLab not connected. | AMBER | No commit/PR evidence can be tied automatically to Jira. | Connect GitHub only if a real EcoGrow repository exists. Do not create a fake repository just to populate metrics. | Engineering / BA
AUD-12 | Story points / velocity | Section 6; Jira Sprint reports/screenshots | Story points are assigned by the real delivery team during Sprint Planning. | No story point estimates are configured; velocity is therefore not calculable. | AMBER | Velocity reporting is structurally present but not meaningful yet. | Estimate Sprint 2 work only if a real planning/estimation activity can be evidenced; otherwise retain as an explicit gap. | Scrum Master / Team
AUD-13 | Sprint dates | Section 6; Jira Sprint reports/screenshots | Real sprint dates should reflect actual sprint boundaries. | Jira displays the same Aug 19–Sep 2, 2026 range for Sprint 1 and Sprint 2. | AMBER | Sprint reporting chronology is ambiguous. | Correct dates before Sprint 3 begins; do not rewrite historical facts. | Scrum Master / BA
AUD-14 | Sprint 2 scope control | Sprint 2 report; Jira screenshot | Sprint goal: Harvest Tracker planting/harvest logging and extend usage capture. | ECO-7 In Progress, ECO-8 In Progress, ECO-10 To Do; no scope changes recorded. | Sprint 2 scope remains aligned; ECO-7/ECO-8/ECO-10 now have evidence and are In Review. | GREEN | The documented Sprint 2 goal covers Harvest Tracker planting/harvest logging and extended usage capture; the three Sprint 2 stories now have evidence. No scope change was recorded. | Proceed to Sprint 2 governance closeout and Sprint 3 readiness without adding unrelated scope. / Scrum Master + PO
AUD-15 | Dependencies | Requirements Engineering; Jira Build Specification; Jira links | FR-06 depends on FR-05; FR-07 depends on FR-05 and FR-06; NFR-03 depends on FR-08. | Dependency chain is documented and Jira links exist for ECO-10 being blocked by ECO-5/ECO-7/ECO-9 in the supplied Jira evidence. | AMBER | Dependency evidence is partly configuration-based; completion still depends on real delivery. | Re-check blockers when ECO-7/ECO-8 move through QA. | BA / Scrum Master
AUD-16 | Governance pack | Latest EcoGrow Governance Pack | Governance registers should be the source of truth and update only from real engagement events. | Stakeholder, RACI, Comms, RTM, Decision, RAID, Benefits, Change Request and Issue Log sheets exist. RTM validation remains 'Not started'. | Governance structure is present; Sprint 2 story evidence has propagated into Section 7, while RTM validation remains open. | AMBER | Section 7 now records Sprint 2 evidence for US-03/US-04/US-06. The RTM itself has not been changed because the complete DoD/validation gate is not yet evidenced. | Finalize RTM only after the remaining validation gate is genuinely satisfied. / BA + Governance
AUD-17 | Decision register | Governance Pack Decision Register | Delivery decisions affecting requirements/golden thread receive DEC IDs. | DEC-03 and DEC-04 document Sprint 2 AC decisions for ECO-7/ECO-8. | GREEN | Decision trace is present. | Use these decisions as evidence of AC definition, not as proof of implementation. | BA / PO
AUD-18 | RAID / issue control | Governance Pack RAID Log; Issue Log | Real risks/issues are logged; issue log should populate when defects are found. | RISK-01 to RISK-04 are documented; Issue Log is empty by design. | GREEN | No defect claim is being invented. | If testing reveals a defect, create an actual Issue/Bug and link it to the story. | BA / QA
AUD-19 | Power BI reporting | Power BI Build Specification; Benefits Register | Pre-operational dashboard may show measurement framework; live product metrics require real usage data. | Benefits actuals remain pending operational data; delivery reporting from Jira can be live independently. | AMBER | Do not present fabricated adoption/usage KPIs. | Build/maintain the measurement framework now; activate product-usage reporting only when FR-08 generates real data. | BA / BI
AUD-20 | Portfolio-grade implementation evidence | Locked EcoGrow build rules; current Jira evidence | No placeholders, filler or invented evidence; every artefact must have business purpose. | Portfolio implementation/prototype evidence is now available for ECO-5, ECO-6, ECO-7, ECO-8 and ECO-10. | GREEN | Controlled portfolio prototypes and evidence now exist for the five evidenced stories. This does not claim a production EcoGrow application or a connected source repository. | Preserve the prototype boundary and evidence trail; do not represent portfolio prototypes as a production system. / BA + Engineering | BA / Engineering
AUD-21 | ECO-5 / FR-01 acceptance evidence | Jira ECO-5; Section 7; current prototype screenshot + video | FR-01: search by plant name or type returns matching Plant Library entries. | Acceptance evidence is now captured; ECO-5 is In Review with acceptance test PASS and Product Owner Persona outcome recorded. | GREEN | I revalidated the search flow using the portfolio test prototype; a Tomato search returned a matching entry. Evidence is attached to Jira. | Retain ECO-5 in In Review until the remaining formal governance/DoD gates are satisfied. / BA + QA | BA / QA
AUD-22 | ECO-6 / FR-02 acceptance evidence | Jira ECO-6; Section 7; current prototype screenshot | FR-02: viewed plant entry displays a content-verified badge and last-reviewed date. | Acceptance evidence is now captured; ECO-6 is In Review with acceptance test PASS and Product Owner Persona outcome recorded. | GREEN | I revalidated the vetted-content display using the portfolio test prototype; the Content-verified badge and last-reviewed date were visible. Evidence is attached to Jira. | Retain ECO-6 in In Review until the remaining formal governance/DoD gates are satisfied. / BA + QA | BA / QA
AUD-23 | FR-01 / FR-03 / FR-09 acceptance criteria confirmation | Requirements Engineering; Decision Register (DEC-03, DEC-04 pattern) | FR-05 and FR-06 have DEC-based acceptance criteria confirmation; equivalent requirements should follow the same pattern. | FR-01, FR-03, FR-09 acceptance criteria confirmation, pending real Product Owner persona sign-off. | AMBER | No DEC entry exists yet for FR-01, FR-03, or FR-09. Their acceptance criteria live only in prototype and Jira evidence, not a Decision Register entry. This is an open governance action, not an error, it should not be backdated. | Create DEC-05/06/07 together once real Product Owner persona confirmation occurs, then propagate to Section 3.5, RTM, and the three Jira stories in one pass. | BA / PO

## Audit Summary
EcoGrow Delivery Audit, Executive Snapshot
Audit basis | Latest Governance Pack + Requirements Engineering + Jira Build Specification + Section 6 + Section 7 + current Jira screenshots/evidence supplied in the engagement.
Audit standard | No assumptions. No fabricated delivery/test results. Jira status is not treated as acceptance validation.
GREEN | 5
AMBER | 5
RED | 0
Immediate decision gate | Formal Sprint Review / governance closeout | RTM validation / final MVP acceptance
Why | ECO-5, ECO-6, ECO-7, ECO-8 and ECO-10 now have acceptance evidence and Product Owner Persona outcomes; the remaining gates are formal all-persona Sprint Review, complete DoD and final RTM validation. | Do not treat story-level evidence as final MVP acceptance. Keep remaining release-readiness gates open until genuinely satisfied.
Then | Complete formal review and DoD reconciliation → final RTM validation → final MVP product acceptance → Section 8 release readiness. | Section 8 remains a later gate; no release decision is asserted now.

## ECO-8 Revalidation
ECO-8 / FR-06 Final Revalidation
Audit item | Status | Evidence-based update
FR-06 acceptance evidence | GREEN | AC1–AC3 tested PASS; four prototype evidence attachments are recorded in Jira; Sprint Review demonstration recorded.
AUD-06 evidence gap | GREEN | The original missing ECO-8 acceptance-evidence gap is resolved by the current Jira evidence.
Product Owner business validation | GREEN | Product Owner Persona outcome is recorded as “Accepted with follow-up review” after the demonstrated acceptance evidence; formal all-persona Sprint Review is still not independently evidenced.
RTM validation | AMBER | RTM validation remains open pending the remaining formal business-validation/DoD gate.
Definition of Done | AMBER | Acceptance testing and story-level review/persona evidence are recorded; complete DoD is not yet evidenced.
Audit standard | GREEN | No assumptions; no fabricated delivery/test results; Jira status is not treated as acceptance validation.