## README
EcoGrow Governance Pack
Prepared by Doris Frank, Business Analyst
Sheet | Purpose | Status
Stakeholder Register | Personas, roles, interest/power (Section 1.5) | Populated
RACI | Persona-based RACI (Section 1.7) | Populated
Communication Plan | Cadence and channels (Section 1.8) | Populated
RTM | Full golden-thread traceability, BO to Release | Populated to Story level, Validation/Release pending real delivery
Decision Register | Logged engagement decisions | 2 decisions logged, more added as they occur
RAID Log | Risks, Assumptions, Issues, Dependencies | Risks populated from Section 6.7, Issues/Assumptions pending real work
Benefits Register | Success measures per objective (Section 4.4-4.5) | Framework populated, actuals pending operational data
Change Request Register | Template only | Empty, populate as real changes are requested
Issue Log | Template only | Empty, populate as real issues are found
Backlog Prioritisation | MoSCoW and value/complexity (Section 3.4, 4.6) | Populated
Colour legend
Amber fill = pending real engagement input, not yet real data

## Stakeholder Register
Stakeholder Register
ID | Persona | Role | Interest | Power | Engagement Strategy
STK-01 | Product Sponsor Persona | Commissions the engagement, holds budget authority | High | High | Manage closely
STK-02 | Product Owner Persona | Owns backlog priority, represents the business voice | High | High | Manage closely
STK-03 | Engineering Lead Persona | Represents the full-stack development team | High | Medium | Keep satisfied
STK-04 | UX Lead Persona | Represents UI/UX design | High | Medium | Keep satisfied
STK-05 | QA Lead Persona | Represents quality assurance | Medium | Medium | Keep informed
STK-06 | Scrum Master Persona | Facilitates ceremonies, protects delivery cadence | Medium | Medium | Keep informed
STK-07 | Gardener Persona (End User) | Represents home and community gardeners, the primary users of EcoGrow's Plant Library, Harvest Tracker, and Community Forum capabilities | High | Low | Keep informed
STK-08 | Support Persona | Supports users experiencing issues with EcoGrow once the product is operational | Medium | Low | Keep informed

## RACI
RACI
Activity | Sponsor | Product Owner | Eng Lead | UX Lead | QA Lead | Scrum Master | Gardener | Support
Define business objectives | A | R | C | C | I | I | I | I
Approve requirements baseline | A | R | C | C | C | I | I | I
Prioritise backlog | I | A/R | C | C | I | I
Sprint planning | I | C | R | R | C | A
Sprint review sign-off | C | A | R | R | R | I | I | C
Go/No-Go decision | A | R | C | C | C | I | I | C

## Communication Plan
Communication Plan
Audience | Cadence | Channel | Owner
Product Sponsor | Monthly | Steering summary | Business Analyst
Product Owner | Weekly | Backlog review | Business Analyst
Delivery team | Daily / per sprint cadence | Standup, sprint ceremonies | Scrum Master persona
All stakeholders | End of each sprint | Sprint review | Product Owner persona
Gardener (End User) | Ongoing, via usage data and Community Forum feedback | Usage analytics, in-product feedback | Business Analyst
Support Persona | Once operational, ongoing | Operational handover documentation, escalation channel | Product Owner persona

## RTM
Requirements Traceability Matrix
This is the master traceability sheet. Validation Status and Release columns (amber) update as Sections 6-8 complete.
Business Objective | Requirement | Epic | Feature | User Story | Acceptance Criteria Ref | Validation Status | Release
BO-01 | REQ-01 / BR-01 | EPIC-01 | FEAT-01, FEAT-02 | US-01 | FR-01, prototype walkthrough completed using the ECO-5 portfolio test prototype, formal acceptance/UAT and RTM validation pending | In progress | MVP
BO-01 | REQ-01 / BR-01 | EPIC-01 | FEAT-02 | US-02 | FR-02, prototype walkthrough completed using the ECO-6 portfolio test prototype, formal acceptance/UAT and RTM validation pending | In progress | MVP
BO-03 | REQ-03 / BR-03 | EPIC-02 | FEAT-03 | US-03 | FR-05: AC1 (plant type), AC2 (planting date), AC3 (planting event), confirmed via DEC-03. Evidence: prototype walkthrough completed against AC1-AC3, all three demonstrated using the ECO-7 portfolio test prototype, supporting evidence attached to Jira. Formal acceptance/UAT and final validation remain pending, FR-05 is not yet considered fully validated. | In progress | MVP
BO-03 | REQ-03 / BR-03 | EPIC-02 | FEAT-04 | US-04 | FR-06: AC1 (planting selection), AC2 (harvest recording), AC3 (planting-to-harvest linkage), confirmed via DEC-04. Evidence: prototype walkthrough completed against AC1-AC3 using the ECO-8 portfolio test prototype. Formal acceptance/UAT and final validation remain pending, FR-06 is not yet considered fully validated. | In progress | MVP
BO-02 | REQ-02 / BR-02 | EPIC-03 | FEAT-05 | US-05 | FR-03, prototype walkthrough completed using the ECO-9 portfolio test prototype, formal acceptance/UAT and RTM validation pending | In progress | MVP
BO-04 | REQ-04 / BR-04 | EPIC-04 | FEAT-07 | US-06 | FR-08, prototype walkthrough completed using the ECO-10 portfolio test prototype (canonical: the three-capability build covering Plant Library and Harvest Tracker's planting and harvest actions, two of the three required capabilities), plus supplementary Community Forum usage-event evidence completing coverage of the third. Formal acceptance/UAT and RTM validation pending. | In progress | MVP
BO-04 | REQ-05 / FR-09 | EPIC-04 | FEAT-08 | US-07 | FR-09, prototype walkthrough completed using the ECO-12 portfolio test prototype, formal acceptance/UAT and RTM validation pending | In progress | MVP (post-harvest prompt only)

## Decision Register
Decision Register
ID | Decision | Date | Made By
DEC-01 | Run requirements elicitation and root-cause analysis before drafting backlog structure, rather than working backward from the brief's mention of Jira | Section 1 | Business Analyst
DEC-02 | Represent stakeholder engagement through defined personas rather than named individuals, for confidentiality reasons specific to this engagement | Section 1 | Business Analyst
DEC-03 | Confirm FR-05 acceptance criteria for US-03 / ECO-7 based on the approved requirement that a gardener can log a planting event, including plant type and date. The confirmed criteria cover plant type capture, planting date capture, and successful logging of the planting event, and will be used as the basis for acceptance testing. | Sprint 2 | Product Owner Persona
DEC-04 | Confirm FR-06 acceptance criteria for US-04 / ECO-8 based on the approved requirement that a gardener can record a harvest against a previously logged planting. The confirmed criteria cover selection of an existing planting, recording the harvest against that planting, and maintaining the planting-to-harvest linkage, and will be used as the basis for acceptance testing. | Sprint 2 | Product Owner Persona

## RAID Log
RAID Log
Risks below are populated from Section 6.7. Assumptions, Issues, and further Dependencies are added as the real engagement surfaces them.
Type | ID | Description | Impact | Owner | Status
Risk | RISK-01 | Three sprints require 6 weeks minimum elapsed time; if the engagement timeline compresses this, MVP scope needs re-negotiation with the Product Sponsor persona | High | Business Analyst | Open
Risk | RISK-02 | US-06 depends on three other stories; if any slip, BO-04's data baseline is delayed | Medium | Business Analyst | Open
Risk | RISK-03 | US-05 is the only MVP story not yet broken into sub-tasks; needs refinement before Sprint 3 planning | Low | Business Analyst | Open
Assumption |  |  |  |  | Pending real engagement input
Issue |  |  |  |  | Pending real engagement input
Dependency |  |  |  |  | Pending real engagement input
Risk | RISK-04 | Sprint 1 and Sprint 2 currently display identical dates (Aug 19-Sep 2, 2026) in Jira Sprint Reports, a configuration inconsistency discovered during Sprint 1 close-out | Low | Business Analyst | Open

## Benefits Register
Benefits Register
Actuals are pending operational data, per the locked Power BI rule for this engagement.
Objective | Success Measure | Benefit Owner | Review Point | Actual
BO-01 | Search-to-view completion rate | Product Owner Persona | First full month post-launch | Pending operational data
BO-02 | Percentage of posts receiving a response within 48 hours | Product Owner Persona | First full month post-launch | Pending operational data, and Phase 2 response feature
BO-03 | Percentage of logged plantings reaching a logged harvest | Product Owner Persona | First full month post-launch | Pending operational data
BO-04 | Usage data completeness and reliability | Product Sponsor Persona | Ongoing, reviewed quarterly | Assessed from first data capture

## Change Request Register
Change Request Register
Empty by design. Populate only when a real change request is raised during delivery (Section 6.11).
ID | Change Requested | Raised By | Impact Assessment | Decision | Date

## Issue Log
Issue Log
Empty by design. Populate only when a real issue is found during delivery or QA.
ID | Issue | Severity | Raised By | Status | Date

## Backlog Prioritisation
Backlog Prioritisation Register
MoSCoW Summary
Requirement | MoSCoW | Business Value | Complexity | MVP Decision | Must
FR-01 | Must | High | Medium | In | Should
FR-02 | Must | High | Medium | In | Could
FR-03 | Should | Medium | Medium | Partial, posting only
FR-04 | Should | Medium | Medium | Out of MVP
FR-05 | Must | High | Low | In
FR-06 | Must | High | Low | In
FR-07 | Could | Medium | Medium | Out of MVP
FR-08 | Must | High | Low | In
FR-09 | Should | High | Low | In (post-harvest prompt only, library variant deferred)