## Success Measures
EcoGrow, Pre-Operational Success Measures Framework
Business Objective | Success Measure | Owner | Review Point | Current Actual | Status
BO-01 | Search-to-view completion rate | Product Owner Persona | First full month post-launch | Pending operational data | Pre-operational
BO-02 | % of posts receiving a response within 48 hours | Product Owner Persona | First full month post-launch | Pending operational data + Phase 2 response feature | Pre-operational
BO-03 | % of logged plantings reaching a logged harvest | Product Owner Persona | First full month post-launch | Pending operational data | Pre-operational
BO-04 | Usage data completeness and reliability | Product Sponsor Persona | Ongoing, reviewed quarterly | Assessed from first data capture | Pre-operational

## Benefits Framework
EcoGrow, Benefits Tracking Framework (Pre-Operational)
Objective | Measure | Target / Direction | Data Source | Review Cadence | Actual | Readiness
BO-01 | Search-to-view completion rate | Target defined in Section 4 | Plant Library usage events | First full month post-launch | Pending | Framework only
BO-02 | Response within 48 hours | Target defined in Section 4 | Forum response events / Phase 2 capability | First full month post-launch | Pending | Framework only
BO-03 | Plantings reaching harvest | Target defined in Section 4 | Harvest Tracker events | First full month post-launch | Pending | Framework only
BO-04 | Usage data completeness and reliability | Target defined in Section 4 | FR-08 usage events | Quarterly after launch | Pending | Framework only

## Delivery Reporting
EcoGrow, Jira Delivery Reporting Framework
Report Element | Source | Current Position | Can Report Now? | Evidence / Note | Owner | Next Action
Sprint Progress | Jira board | Sprint delivery status available from Jira | Yes | Engagement delivery reporting, not product usage | Business Analyst | Keep aligned to Jira status
Velocity | Jira sprint data | Meaningful from Sprint 2 onward when estimates exist | Conditional | Story points are currently not evidenced for the reviewed stories | Business Analyst / Delivery Team | Use only when real estimates exist
Burndown | Jira sprint data | Available per sprint when sprint data is configured | Conditional | Do not treat as functionality evidence | Scrum Master persona | Review alongside sprint execution evidence
Defects | Jira Bugs | Only report when real Bugs are logged | No live defects claimed | Build specification says Bugs are created only when real defects are found | QA Lead persona | Log genuine defects if found
Release Status | Jira / EcoGrow MVP version | MVP release exists as the single release strategy | Yes | Release status is delivery reporting; not release approval | Business Analyst | Update from Jira when release gate changes
Product Usage | FR-08 usage events | No live production reporting layer implemented | No | Do not fabricate product-usage actuals | Product Sponsor Persona | Build post-operational reporting when real usage data exists

## Reporting Roadmap
EcoGrow, Reporting Roadmap
Stage | Build | Purpose | Data Condition | Governance Rule
Pre-Operational | Success Measures + Benefits Framework + Jira Delivery Reporting | Establish measurement structure without live product results | No production usage data required | No live business actuals before operation
Post-Operational | Product Adoption + Weekly Active Users + Feature Usage + Satisfaction + Retention + Benefits | Monitor real product performance and benefits | Real usage data available | Replace framework placeholders with actuals
Future Enhancement | Refine metrics and add formally prioritised Phase 2 capabilities | Evolve reporting based on real usage and approved scope | Formal reprioritisation required | No Phase 2 scope leakage into MVP